## Sheet1
| Name: | Jess Totorica |  |  | Date: | 2020-01-23
Weekly Action Items
1 | Extend J1 cpu instruction width to 18 bits
2 | Restructure J1 verilog, come up with new name
3 | Continue working on assembler
4 | Start designing a VGA interface for a Pong game
5 | Begin writing Pong in Forth
6
7
8
9
10
Summary of Progress
The Forth assembler, written in Python, is in progress. Changes to the J1 core have begun to add the ability to use relative jumps/calls. Still needs testing.
Meeting Attendance: |  |  |  | Was Meeting Helpful? | Yes
Name: |  | P | NP
Kyle Hartman: |  | x |  | If No Why?
Thys Ballard: |  | x
Jess Totorica: |  | x
Kyle Hild |  | x
Ronald Crump: |  | x
Team Member Contributions:
Kyle Hartman: |  | Researching VGA hardware implementation
Thys Ballard: |  | Researching compiler
Jess Totorica: |  | Starting to debug changes to J1
Kyle Hild: |  | Making good progress on assembler
Ronald Crump: |  | Will start working on Pong code