## Sheet1
| Name: | Thys Ballard |  |  | Date: | 2020-03-26
Weekly Action Items
1 | Discuss current status of project
2 | Discuss current to-do items
3 | Discuss next steps (in light of quarantine)
4
5
6
7
8
9
10
Summary of Progress
Discussed current state of the hardware and software components. Currently, the VGA interface is still being worked. The assembler is more or less complete, but more testing is needed. The VGA interface and the compiler are still yet to be done. Next steps are to get a hold the hardware for the project, since we don’t have access to the drone lab anymore. Kyle Hartman will keep the hardware at his place.
Meeting Attendance: |  |  |  | Was Meeting Helpful? | x
Name: |  | P | NP
Kyle Hartman: |  | x |  | If No Why?
Thys Ballard: |  | x
Jess Totorica: |  | x
Kyle Hild |  | x
Ronald Crump |  |  | x
Team Member Contributions:
Kyle Hartman: |  | Discussed VGA interface
Thys Ballard: |  | Discussed next steps for compiler
Jess Totorica: |  | Discussed VGA interface
Kyle Hild: |  | Discussed assembler
Ronald Crump |  | N/A